|  |
| --- |
|   |
|   | **IICSA Recommendation 5 Safeguarding and HR Information sharing agreements.** |   | **IICSA Recommendation 6 Information-sharing between the Church of England, Church in Wales, and Police.** |   | **IICSA Recommendation 6 Information-sharing between the Church of England, Church in Wales, and statutory partners ( not police)**  |   |
|   | **Complete**  | April 2021 Draft data sharing agreement and framework being developed  |   | **Complete**  | August 2022 Working with OP Hydrant to develop draft data sharing agreement  |  | **In progress**  | March - Oct 2022 Define Phase  |   |
|  |   |   |   |  |   |   |
|  | **Complete**  |  June 2021 Consult with other relevant departments  |   | **Complete**  | September 2022 working with interested parties to validate the draft data sharing agreements  |  |   | Nov 22 - Jan 23 Plan and design  |   |
|  |   |   |   |  |   |   |
|   | **Complete**  | September 2021 Take legal advice on the draft agreements and framework  |   | **Complete**  | October 2022 Police complete their consultation process  |  |   |   |   |
|   |   |   |   |  |   |   |
|   | **Complete**  |  December 2021 Conduct feedback workshops with relevant parties  |   | **Complete**  | November 2022 Church of England complete their consultation process  |  |   |   |   |
|   |   |   |   |  |   |   |
|   | **Complete**  | February 2022 Redraft agreements  |   | **Complete**  | January 2022 Heads of department sign off ISA  |  |   |   |   |
|   |   |   |   |  |   |   |
|   | **Complete**  |  April 2022 Validation process with final drafts  |   | **In progress**  | February 2023 Documents sent out to dioceses and cathedrals for signing  |  |   |   |   |
|   |   |   |   |  |   |   |
|   | **Complete**  | June 2022 Heads of department sign off ISA and framework  |   |   | May 2023 All documents signed  |  |   |   |   |
|   |   |   |   |  |   |   |
|   | **Complete**  | July 2022 Documents sent out to dioceses and cathedrals for signing  |   |   |   |  |   |   |   |
|   |   |   |   |  |   |   |
|   | **Complete**  | December 2022 All documents signed  |   |   |   |  |   |   |   |