|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | | | | | | | | | | |
|  | **IICSA Recommendation 5 Safeguarding and HR Information sharing agreements.** | |  | **IICSA Recommendation 6 Information-sharing between the Church of England, Church in Wales, and Police.** | |  | **IICSA Recommendation 6 Information-sharing between the Church of England, Church in Wales, and statutory partners ( not police)** | | |  |
|  | **Complete** | April 2021 Draft data sharing agreement and framework being developed |  | **Complete** | August 2022 Working with OP Hydrant to develop draft data sharing agreement |  | | **In progress** | March - Oct 2022 Define Phase |  |
|  |  | |  |  | |  |  | | |  |
|  | **Complete** | June 2021 Consult with other relevant departments |  | **Complete** | September 2022 working with interested parties to validate the draft data sharing agreements |  | |  | Nov 22 - Jan 23 Plan and design |  |
|  |  | |  |  | |  |  | | |  |
|  | **Complete** | September 2021 Take legal advice on the draft agreements and framework |  | **Complete** | October 2022 Police complete their consultation process |  | |  |  |  |
|  |  | |  |  | |  |  | | |  |
|  | **Complete** | December 2021 Conduct feedback workshops with relevant parties |  | **Complete** | November 2022 Church of England complete their consultation process |  | |  |  |  |
|  |  | |  |  | |  |  | | |  |
|  | **Complete** | February 2022 Redraft agreements |  | **Complete** | January 2022 Heads of department sign off ISA |  | |  |  |  |
|  |  | |  |  | |  |  | | |  |
|  | **Complete** | April 2022 Validation process with final drafts |  | **In progress** | February 2023 Documents sent out to dioceses and cathedrals for signing |  | |  |  |  |
|  |  | |  |  | |  |  | | |  |
|  | **Complete** | June 2022 Heads of department sign off ISA and framework |  |  | May 2023 All documents signed |  | |  |  |  |
|  |  | |  |  | |  |  | | |  |
|  | **Complete** | July 2022 Documents sent out to dioceses and cathedrals for signing |  |  |  |  | |  |  |  |
|  |  | |  |  | |  |  | | |  |
|  | **Complete** | December 2022 All documents signed |  |  |  |  | |  |  |  |