## Sheet1
EXAMPLE ASSET MANAGEMENT PLAN (AMP)
By combining real tasks and costs of Regular Maintenance with projected tasks and costs of Capital Repairs, Improvements & New Works, the AMP produces annual and long term budgets for the building, enabling both preventative maintenance and saving for large capital items.
| KNOWN | COST per | ANNUAL | Year Intervals | [7 empty] | COST over
| CYCLE | CYCLE | COST | 2 | 5 | 10 | 15 | 20 | 25 | 30 | other | 30 YEARS
REGULAR MAINTENANCE
Clean Gutters and Downpies | 3 months | 200 | 800 | [8 empty] | 24000
Clean Gullies and drains | 3 months | 50 | 200 | [8 empty] | 6000
Boiler Service | annual | 200 | 200 | [8 empty] | 6000
Ventilation Service | annual | 200 | 200 | [8 empty] | 6000
Portable Electric Appliances Test | annual | 125 | 125 | [8 empty] | 3750
Vermin and Rodent Control | 3 months | 70 | 280 | [8 empty] | 8400
Cleaning window glass | 2 yr | 500 | 250 | [8 empty] | 7500 | bar: Year Intervals 2
Lightning Conductor Test | 2 yr | 100 | 50 | [8 empty] | 1500 | bar: Year Intervals 2
Fire Extinguisher Test/replacement | annual | 150 | 150 | [8 empty] | 4500
Electrical Installation Test | 5 yr | 3000 | 600 | [8 empty] | 18000 | bar: Year Intervals 5 to Year Intervals 30
Painting Exterior metal/wood | 5 yr | 5000 | 1000 | [8 empty] | 30000 | bar: Year Intervals 5 to Year Intervals 30
Churchyard Grass-mower service, fuel | annual | 300 | 300 | [8 empty] | 9000
Churchyard Landscape/Trees | annual | 500 | 500 | [8 empty] | 15000
Churchyard walls pointing & clear ivy | 5 yr | 1000 | 200 | [8 empty] | 6000 | bar: Year Intervals 5 to Year Intervals 30
Repointing Various Areas | 2 yr | 3000 | 1500 | [8 empty] | 45000 | bar: Year Intervals 2
Total |  |  | 6355 | [8 empty] | 190650
CAPITAL REPAIRS |  |  |  | Year Intervals 2: When work will be required
Churchyard Paths | 10 yr | 5000 | 500 | [8 empty] | 15000 | bar: Year Intervals 5; Year Intervals 15; Year Intervals 25
Felt roofs to boiler roof and organ loft | 20 yr | 10000 | 666 | [8 empty] | 20000 | bar: Year Intervals 10; Year Intervals 30
Repair/replace window feramenta | as & when | 3000 | 300 | [8 empty] | 9000 | bar: Year Intervals 10; Year Intervals 20; Year Intervals 30
North Aisle Mullions | 100+ yr | 25000 | 834 | [8 empty] | 25000 | bar: Year Intervals 15
Pinnacles to tower | 100+ yr | 60000 | 2000 | [8 empty] | 60000 | bar: Year Intervals 20
High Level Internal Cleaning | 10 yr | 3000 | 300 | [8 empty] | 9000 | bar: Year Intervals 5; Year Intervals 15; Year Intervals 25
Lead Roofs patch repair | 10 yr | 3000 | 300 | [8 empty] | 9000 | bar: Year Intervals 10; Year Intervals 20; Year Intervals 30
Lead roof replace (100 years old) | 150 yr | 150000 | 3000 | [7 empty] | 50 | 90000
Electric Lighting upgrade | 25 yr | 25000 | 833 | [8 empty] | 25000 | bar: Year Intervals 25
Electric Power upgrade | 25yr | 15000 | 500 | [8 empty] | 15000 | bar: Year Intervals 25
Heating & Boiler upgrade | 25 yr | 35000 | 1166 | [8 empty] | 35000 | bar: Year Intervals 25
Kitchen & Toilets upgrade | 15 yr | 12000 | 800 | [8 empty] | 24000 | bar: Year Intervals 15; Year Intervals 30
Ventilation System Replace | 20 yr | 18000 | 600 | [8 empty] | 18000 | bar: Year Intervals 20
Total |  |  | 11799 | [8 empty] | 354000
IMPROVEMENTS & NEW WORKS |  |  |  | Year Intervals 2: Project Target Completion
Fire Alarm & Emergency lights install | one off | 18000 | 3600 | bar: Year Intervals 5
Re-ordering, new rooms & office | one off | 130000 | 13000 | bar: Year Intervals 10
New Mower | one off | 500 | 100 | bar: Year Intervals 5
Total |  |  | 16700
AMP annual total (£) to be raised: |  |  | 34854